## Sheet1
	Activity	Description	Deliverables/Checkpoints	Duration (days)	People	Resources	Predecessors
1	Hardware Design
1.1	Plan Switch Configuration	Design a basic plan for the keyboard, specificially the placement of the switches.	Initial product design sketch	7	Chris
1.2	Design Circuitry	Design the circuit necessary in order implement the planned switch placement	Circuit schematic	1	Chris		1.1
1.3	Purchase Components			7	Chris		1.1
1.4	Construct Prototype	Build and test our prototype.
1.4.1	Construct a base	Construct a platform which holds our microprocessor and switches, the switches are to be aligned based on our initial product sketch.		7	Chris, Trey		1.3
1.4.2	Apply the Circuit	Connect the switches to the microprocessor through use of the schematic designed earlier.		2	Trey		1.4.1
1.4.3	Provide a method of activating each switch	Add a device between the switches which allows each one to be activated.		5	Chris, Trey		1.4.1
1.5	Program Prototype
1.5.1	Establish Input	Read input from each switch on the microcontroller	Test data	1	Trey, Bryant		1.4.2
1.5.2	Interpret Input	Program the character representation for each input from the keyboard.	Test data	2	Trey, Mike, Bryant		1.5.1
1.5.3	Configure Output	Output the character last input from the keyboard to the client.	Test data	5	Trey, Bryant
2	Software Design
2.1	Research Software	Research available opensource software for both text prediction and text to speach applications		14	Mike
2.2	Software Planning
2.2.1	Plan Text Prediction	Either plan a new text prediction program from scratch or plan how to reimpliment existing opensource software.	Flowchart and program description for text prediction				2.1